## Sheet1
Id | User story | Acceptance criteria | Points | Status
1 | As a user I want to open the application | - tap on icon in application list to open app; - application should display a tab view with the following entries: Tools, Library; - the default selection should be Tools; | 3 | Done
2 | As a user I want to select Tools and see a list of available tools | - tapping on Tools in tab view should display the list of available tools on the page; - the available tools should be displayed as buttons on screen, divided in 2 sections: Settings, Start/Stop function; - the following entries should be available in settings area: Video recorder, Audio recorder, Call recorder, Encryption, Security; - the following entries should be available in the start/stop function area: Enable video recording, Enable audio recording, Enable call recording; - the bottom of the page should have a help button; | 5 | Done
3 | As a user I want to select Library and see a list of all recordings that were taken | - tapping on Library should display the list of recordings taken; - under the tab view there should be filters for recording type and date (maybe name too?); - every entry in the list should have a name, an icon/thumbnail, the date it was recorded and length; - the recording types are: Video, Audio, Call; | 8 | Estimated
4 | As a user I want to select Tools then select Video recorder settings and see the related settings | - tapping on Video recorder should display a list of video recording settings; - the following settings should be displayed: - buttons to select either rear or front camera to use (should be greyed out if any of them not available); - recording quality settings based on camera capabilities (resolution, fps); - recording length: fixed time or unlimited (until app runs out of space); - recording start/stop trigger: manual, shake, voice activated; | 8 | Estimated
5 | As a user I want to select Audio recorder settings and see related settings | - tapping on Audio recorder should display a list of audio recording settings; - the following settings should be displayed: - recording quality (frequency, bits, or maybe just low,medium,high); - recording length: fixed time or unlimited (until app runs out of space); - recording start/stop trigger: manual, shake, voice activated; | 8 | Estimated
6 | As a user I want to select Call recorder settings and see related settings | - tapping on Call recorder should display a list of call recording settings; - the following settings should be displayed: - same settings as Audio recording; | 8 | Estimated
7 | Build background service to listen for events and start/stop recordings based on user settings | - background service to listen for shake/voice/widget input to start/stop recordings based on application settings; - creation of relevant classes to handle recording and storing; | 13 | In Progress